## 2025 Cost Baseline
2025 Cost ($) | Notes
80000 | New booth model
1500 | Same as 2021
500 | Same
150 | Same
150 | Same
1000 | Same
1400 | Same
1200 | Same
5000 | Same
2000 | +33% increase
3200 | +60% increase
8000 | +60% increase
| Total | 104100
Activity | Weekly Cost ($) | Cumulative Cost ($)
Booth Deposit (50%) | 40000 | 40000
Permits + Inspection | 5900 | 45900
Facility Prep Start | 2500 | 48400
Facility Prep & Rentals | 4500 | 52900
Booth Delivery | 0 | 52900
Installation (Part 1) | 1600 | 54500
Installation (Part 2) | 1600 | 56100
Sprinkler Install (Part 1) | 4000 | 60100
Sprinkler Install (Part 2) | 4000 | 64100
Testing & Operate Permit | 1200 | 65300
Final Booth Payment | 40000 | 105300
Project Closeout | 0 | 105300
Buffer / Contingency | 0 | 105300